## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Worth the Words
Binary Bunch
Cora A, Nick F, Becca G, Ben L, Alex W
Project start date: | 2025-01-27 | [9 empty] | Scrolling increment: | [5 empty] | 0
|  |  |  | January | [6 empty] | February | [27 empty] | March
 | time axis 2025-01-27 to 2025-03-23
Milestone description | Assigned to | Start | Days | time axis 2025-01-27 to 2025-03-23
User Flow Diagram | Nick Frondorf | 2025-01-27 | 7
Systems Architecture Diagram | Alex Welsh | 2025-01-27 | 7
Entity Relationship Diagram | Cora Alward | 2025-01-27 | 7
Project Charter | Becca Gossett | 2025-01-27 | 7
Statement of Work | Alex Welsh | 2025-01-30 | 6
Project Status Report 1 | Binary Bunch (Team) | 2025-02-03 | 7
Event Calendar V1 | Becca Gossett | 2025-02-10 | 21
Community Partners V1 | Becca Gossett | 2025-02-10 | 21
Donation Module V1 | Ben Leonard | 2025-02-10 | 21
Volunteer Sign-up V1 | Nick Frondorf | 2025-02-10 | 21
Contact Form V1 | Cora Alward | 2025-02-10 | 21
Landing Page / Project Showcase V1 | Alex Welsh | 2025-02-10 | 21
Summary of Dev Progress | Binary Bunch (Team) | 2025-02-10 | 21
Event Calendar V2 | Becca Gossett | 2025-03-03 | 29
Community Partners V2 | Alex Welsh | 2025-03-03 | 29
Donation Module V2 | Ben Leonard | 2025-03-03 | 29
Volunteer Sign-up V2 | Nick Frondorf | 2025-03-03 | 29
Contact Form V2 | Cora Alward | 2025-03-03 | 29
Landing Page / Project Showcase V2 | Alex Welsh | 2025-03-03 | 29
Project Status Report 2 | Binary Bunch (Team) | 2025-04-01 | 5
Requirement Traceability Matrix - Latest Version | Binary Bunch (Team) | 2025-04-01 | 5
Final Event Calendar | Becca Gossett | 2025-04-06 | 16
Final Donation Module | Ben Leonard | 2025-04-06 | 16
Final Volunteer Sign-up | Nick Frondorf | 2025-04-06 | 16
Final Contact Form | Cora Alward | 2025-04-06 | 16
Final Project Showcase | Alex Welsh | 2025-04-06 | 16
Final Homepage | Becca Gossett & Alex Welsh | 2025-04-06 | 16
Final Shop Page | Ben Leonard | 2025-04-06 | 16
Final About Us | Various Members | 2025-04-06 | 16
Final Footer | Becca Gossett & Alex Welsh | 2025-04-06 | 16
Final Mobile View | Alex Welsh | 2025-04-06 | 16
Final Project Status Report | Binary Bunch (Team) | 2025-04-22 | 5
Final Requirement Traceability Matrix | Binary Bunch (Team) | 2025-04-22 | 5
Final Project Management Plan | Binary Bunch (Team) | 2025-04-22 | 5